## Problem Chart
GLOBE FISHERIES LIMITED
ERP FINDINGS
DATE : 25th February 2023
SL | Module | Sub-Module | Link | Point | Requirement | Comment Box | Status
1 | Product Management | Product List > Add Product | https://globefisherp.com/admin/products | Product Name | The list shown on the dropdown menu need to be clear with details for avoiding any conflicts | Need to discuss.(Multiple grade error) | done
|  |  |  | Product Image | Attachment is not mandatory | Ok | done
|  | Product List > Edit |  | Product Image | Re-Upload is not working | OK | done
|  | Product List |  | Product List | Arrange the column in the following serial: SL, Image, Product Code, Type/Category, Product Name, Grade, Packsize, Variant, Inhouse Selling Price, Online Selling Price. | ok | working
[5 empty] | Search Bar error (Auto USER ID is displayed) | OK | done
2 | Client Management | Create Client | https://globefisherp.com/admin/party/create | Add Product | Show All details of the product when selected | OK | done
[5 empty] | Product selection and price entry can be done any time | Need to discuss with authrority ( NEEd to do R&D) | done
[5 empty] | Primary Product Name: Market Name Secondary Product Name: Product Name | OK | done
|  | Client List | https://globefisherp.com/admin/party-management?customer_type=Online | Part/Online/Inhouse | Search option Missing | OK | done
|  | Create Client/Client List | Both Panel | Party | Title Rename: rename "PARTY" into "Modern Trade" | OK | done
3 | Requisition | Request Requisition | https://globefisherp.com/admin/requisition | Product | Show All details of the product when selected | OK | done
|  |  |  | Grade | Missing | Need to discuss(Add new requisition) | done
|  |  |  | Variant | Missing | Need to discuss(Add new requisition) | done
|  |  |  | Pending Requisition > Individual Product "EDIT" | Title Rename: "NAME" & "CODE" misplaced, Need to Switch the Title | ok | done
|  |  |  | Action > Print | THE FOLLOWING INFORMATION ARE MISSING: Requisition Info: Barcode, Requisition Code (shown wrong number), Party Code, Remark, Product Info: Product Code, Grade, Variant Primary Product Name: Market Name Secondary Product Name: Product Name Information NOT REQUIRED: Provided Quantity, Balanced Quantity | ok | done
|  |  |  | Add Product | Show All details of the product before and after selected | Allready done. Need to discuss.( Product dropdown bar information details) | done
[5 empty] | Title Rename: "NAME" & "CODE" misplaced, Need to Switch the Title | OK | done
|  |  |  | ERROR | AUTO CONFIRMING. | Need to R&D
|  | Recent Requisition | https://globefisherp.com/admin/requisition?status=Processing | Proccessing Request | Not Required: Edit button & Delete Button | ok | done
|  |  | https://globefisherp.com/admin/requisition | All Tabs | Title for each tabs have not been changed. All of them are using the same title. Please change the title for each tab as they are selected. | Need to discuss( Tab name by selected tab) | done
|  |  | https://globefisherp.com/admin/requisition-receive?status=Returned | Return Request | When selected it directed me to a different page and changes its interface, all the tab from the top are gone and it shows that I am in the dispatch Requisition panel or something. | Need to R&D( Tab name by selected tab) | done
|  |  | https://globefisherp.com/admin/requisition | All Tabs | Arrange the column in the following serial inside "Product": SL, Product Code, Type/Category, Product Name, Grade, Packsize, Variant, Quantity in (PKT), Quantity in (KG), Action. (ETC) | ok | done
4 | DO | Create DO | https://globefisherp.com/admin/requisition-dispatch-order | Column Serial | SL, Requisition Code, Warehouse Name, Party Code, Party Name Status, Order Date, Expected Date, Remark, Payment Info, Products {SL, Product Code, Type/Category, Product Name, Grade, Packsize, Variant, Requested Quantity (PKT & KG), Provided Quantity (PKT & KG), Balance Quantity (PKT & KG).}, Action | Ok | done
|  |  |  | Create DO | Column Serial: SL, Product Code, Type/Category, Product Name, Grade, Packsize, Variant, Requested Quantity (KG), Available Stock (KG), DO Quantity (KG) > Input Box Create DO: D.O can be create even if the stock quantity is "O" | OK | done
|  |  |  | Action | Print option missing | ok | done
|  |  | https://globefisherp.com/admin/requisition-dispatch-order/12 | See DO | Required: Cancel Button Not Required: Revised Button Column Serial inside Products: SL, Product Code, Type/Category, Product Name, Grade, Packsize, Variant, DO Request (PKT & KG) Edit: (SL, Product Code, Type/Category, Product Name, Grade, Packsize, Variant, Requested Quantity (KG), Available Stock (KG), DO Quantity (KG) > Input Box) | Need to discuss( Revise button will be rename as cancel)
|  | Dispatch Requisition | https://globefisherp.com/admin/requisition-receive | Column Serial | SL, Requisition Code, DO Code, Warehouse Name, Party Code, Status, DO Date, Expected Date, Remark, Products {SL, Product Code, Type/Category, Product Name, Grade, Packsize, Variant, DO Quantity (PKT & KG), Dispatch Quantity (PKT & KG)}, Action | Ok | done
|  |  |  | Provide Quantity Button | Column Serial: SL, Product Code, Type/Category, Product Name, Grade, Packsize, Variant, DO Quantity (KG), Available Stock (KG), Dispatch Quantity (KG) > Input Box Provide Quantity Button: Dispatch Quantity CANNOT BE greater than or less than D.O Quantity or if the stock is not matched with the requirement | Need to do R&D | done
|  |  |  | Revise Button | Add: Remark Box or Text Box | OK | done
|  |  |  | Provide Quantity Button | After production of the required item the Available Stock is not getting updated. It still says "0" Stock available. | Allready made a solution and its uder development | done
5 | Production Management | Configuration > Block Size | https://globefisherp.com/admin/processing-block | Block List | Need to be in Numeric Order (Low to High) | Ok
|  | Configuration > Grade List | https://globefisherp.com/admin/processing-grade | Grade List | Title rename: Block Grade List | Ok
|  | Configuration > Size List | https://globefisherp.com/admin/processing-block-size | Size List | Title rename: Block Size List | Ok
|  |  |  | Add New Size | Title rename: Popup Window (Add New Size) | Ok
|  | Chill Room > Total Stock | https://globefisherp.com/admin/production/chill-room/total-stock | - | Use of this panel is undetected | ok
|  | Supply > Items | https://globefisherp.com/admin/supply-item | Add Item | Market name: Can be kept blank | Ok
[5 empty] | Submit Error: Takes multiple Entry on multiple click | Ok
|  |  |  | Item List | Change Column Title from (Grade Name) to (Grade) | under development . It will not be in the list as we discussed. | done
[5 empty] | Items need to be in Ascending Order | Need to discuss.( A, B,C,D,E…...... I that order)
|  |  |  | Edit | Title rename: Popup Window (Update Item) & Grade option NOT FOUND | OK
|  | Supply > Manage Supplier | https://globefisherp.com/admin/production-supplier | Panel Name | Supplier spelling wrong | OK
|  |  |  | Supplier List | Wrong Title (Item List) > (Supplier List) | Ok
[5 empty] | SL must be in Capital form | OK
[5 empty] | Change (Supplier Mobile) > (Supplier Contact) | Ok
[5 empty] | Title misplaced (Supplier Email) with (Supplier Address) | Ok
|  |  |  | Edit | Wrong Title & editable contents missing | ok
|  | Supply > Requisition > Add Requisition | https://globefisherp.com/admin/production-requisition/create | Expected Date | change format (mm/dd/yyyy) to (dd/mm/yyyy) | OK
|  |  |  | Select Item | after selecting the item from the list, only show the Item NAME under Select Item section | Discussed and emailed(Only name show & grade selectable) | done
|  |  |  | Quantity(KG) | enable entry for faction number | ok(Sub total not adding fractional input)
|  |  |  | Product Chart | serial number column is NOT FOUND | ok
|  | Supply > Requisition > Requisition List | https://globefisherp.com/admin/production-requisition?status=Pending&page=1 | Pending List > Edit | NOT WORKING (when the value are changed) | ok | done
|  |  |  | All tabs | ADD: Requisition Number | ok
|  | Unload Unit | https://globefisherp.com/admin/production/unload/gate_man/raw_item | Raw Item Check IN | Show Date & Time of the Requisition. Show Requisition Number. Check Button: show all information or the order and supplier | ok
|  |  | https://globefisherp.com/admin/production-unload-show | Raw Item Unload | Show Requisition Number & Date. NOTE: No need to show Supplier Information Funtion Error: The figure in Total(KG) gets blank when the input in Return is erased. Calculation Error: When there is any Missing Quantity the value in Total(KG) should be calculated after ajdusting it with Return Quantity. The value in Total(KG) is not changing if the value in other Subjected Box are changed. Excess Quantity is not calculation any value if the receiving quantity is greater than requested quantity. | Need to do R&D
|  | Processing Unit > IQF | https://globefisherp.com/admin/production/processing-unit/iqf | IQF > Fillet > Quantity | Not showing Data after Filleting weight is input | ok
|  |  |  | Soaking Weight | Gained Percentage: Calculation Error Formula: (final - initial) % increase = 100 x ------------------- ¦ initial ¦ e.g. (743 - 300) % increase = 100 x ------------------- ¦ 300 ¦ = 147.66 % | ok | done
|  |  |  | All process Window | Date & Time format: (DD/MM/YYYY, 12 Hours Format) | ok. Need time
|  | Inventory Management > Store > Store In | https://globefisherp.com/admin/inventory/store-in | Quantity(KG) | ERROR: value is not showing as per produced Data | OK | under development(By Sohel Bhai)
|  |  |  | Move to Bulk | Input Value cannot exceed the produced Value | OK | under development(By Sohel Bhai)
6 | Inventory Management | Stock List | https://globefisherp.com/admin/inventory/stock?customer_id=2 | Column: Pack Size | required only single column with only packsize data, no need for (PKT & KG)
|  |  |  | Search Bar | need Auto search when the party is selected
|  |  |  | Same page | Show the selected party code somewhere in that page as a title
7 | Production Management | Supply | https://globefisherp.com/admin/supply-item?page=1 | Items | show 1-50 in each page, and the serial number should continue to next page |  | done